## Using this form
Using this SID risk assessment form
Guidance note -- September 2026 Version 2.8
When to use the form
Use the SID risk assessment form when you’re following the Tiaki Wai Safety in Design Process (HSEP_0014). Update the risk assessment as you progress through the project.
Always start with the controlled template, HSER_0261. Do not start by modifying a risk assessment form used for another project.
SID Risk Assessment Form HSEP_0261
Record management
Save the SID risk assessment in the project folder. The SID process also prompts you to do this.
Filling out the SID risk assessment form
General details
1. Add the date of the risk assessment and use the dropdown menu to identify which project phase you’re working in.
2. Fill out the project details and stakeholders for this phase of the project.
3. Add links to relevant documents.
4. Check these details throughout the project and update them if they change during subsequent phases of the project.
5. Record relevant decisions made.
Raw risk assessment
1. Start by identifying and capturing all the raw (unmanaged) risks in the second half of the worksheet in the ‘Raw risk’ section under the ‘Risk assessment’ heading.
2. Complete all columns unless they are marked ‘N/A.
3. Add the following information for each raw risk.
a. (Optional) Who identified the risk.
b. (If applicable) The asset that the risk relates to.
c. Identify the risk source.
i. The template is already pre-populated with 21 key health and safety risks. You must always consider these during risk assessments. This list includes risks that we must consider under New Zealand regulations. See the 'Guidewords checklist' worksheet for more detail about each type of risk and for links to the regulations.
ii. You may need to split some of the key risks into more than one line to capture, for example, different risks from different chemicals or different risk owners or control owners for different aspects of a risk (for example, the designer is not responsible for construction risks unless the risks result from design choices).
iii. If a pre-populated key risk isn’t applicable, explain why in the ‘Risk description’ field, and select N/A from the dropdown list under Raw consequence. This will automatically grey out the row. Do not delete the row, as you want to show that you considered the risk.
iv. Review the project in detail to identify specific risks, particularly for specialist projects.
v. Check site-specific information, registers and systems, and previous briefs, risk assessments and JSEAs for the asset or similar infrastructure.
vi. Consult the asset manager and operational staff who know the asset well.
vii. Visit the site.
d. Write a short description of each risk.
e. Assign a level of raw (unmanaged) consequence from the drop-down list. For descriptions of the levels of consequence, see the ‘Consequence’ worksheet.
f. Assign a level of raw (unmanaged) likelihood from the drop-down list. For descriptions of the levels of likelihood, see the ‘Likelihood’ worksheet. The likelihood score is independent from the project length. If you’re working on a short project (e.g. less than six months), and assign the likelihood regardless of the project length.
g. The form will calculate the ‘raw risk rating’ automatically.
Discussing risk management in SID meetings
a. Sort the raw risks by 1) selecting all cells in all colums (A through P) under the SID risk assessment headers, 2) selecting
Data/Sort in Excel's ribbon, and 3) sort on column ‘Raw risk rating’ from extreme to low ‘raw risk rating’
b. Add the information for risk management.
c. Choose a control measure from the dropdown list.
i. Selecting 'Minimise' will enable the auto-calculate function.
ii. Selecting 'Eliminate' will grey out the remainder of the row except for the Control description and Risk owner cells, which must be completed, see below.
d. Choose a control type from the dropdown list.
e. Write a short description of the control.
f. If the risk won’t be eliminated by the control, justify the control measure in the ‘Justification’ for control’ column.
g. Identify the control owner. This may change as the project progresses. Keep this up to date.
h. Assign a level of raw consequence from the drop-down list. For descriptions of the levels of consequence, see the ‘Consequence’ worksheet.
i. Assign a level of raw (unmanaged) likelihood from the drop-down list. For descriptions of the levels of likelihood, see the ‘Likelihood’ worksheet. The likelihood is independent from the project length. If you’re working on a short project (e.g. less than six months), and assign the likelihood regardless of the project length.
j. The form will calculate the ‘residual risk rating’ automatically.
k. Assign a risk owner. This may change as the project progresses. Keep this up to date.
If the list of risks becomes very long, you may consider sorting related risks into sections, as long as the process above is followed for sorting them extreme to low raw risk rating per section.

## SID risk assessment
|  | Safety in Design Risk Assessment |  |  | The information in this worksheet is updated as the project progresses. Update the 'Project phase' field to reflects the phase of the project. Take separate meeting minutes to capture specific decisions.
Qpulse document no: HSER_0261 CONTROLLED TEMPLATE
Version 2.8
General details
Detail of this SID risk assessment |  |  | Stakeholders advising on this assessment |  | See SID process for role definitions |  | Record of decisions |  |  | See SID process for decision points | Documents supporting this risk assessment
Meeting/assessment date |  |  | Investigator(s) |  |  |  | SID process Section 2.3 after step 1: "Is another SID meeting needed?": Add link(s) to the recorded decision about holding another SID meeting, or not. |  |  |  | Add links to investigation sources, drawing sets, service plans, design reports, other docs
Project phase |  |  | Designer
Project manager
Operator(s) and maintainer(s)
Project details |  |  | Contractor(s)
Project name |  |  | Property owner(s) |  |  |  | SID process Section 2.3 after step 2b: "Does the SID risk assessment need input from a health and safety specialist?" (HAZOP/CHAZOP). Add link(s) to the recorded decision about this.
Project no. |  |  | Representative(s) | [7 empty] | Guidance
Asset type |  |  | H&S specialist | [7 empty] | How to complete this form ('Using this form' worksheet)
Location/site name |  |  | Other (name and role) | [7 empty] | Safety in design process (PDF)
Risk assessment | [5 empty] | For discussions in SID meetings, sort this column: extreme to low
Raw risk | [6 empty] | Risk management
Risk identified by (optional) | Asset that the risk relates to (if applicable) | Risk source (hazard) | Risk description | Raw consequence | Raw likelihood | Raw risk rating | Control measure | Control type | Control description | Justification for control (if risk not eliminated) | Control owner | Residual consequence | Residual likelihood | Residual risk rating | Risk Owner
|  | Assets or fixed plant |  | Minor 10 | Unlikely 3 | Low 30 | Minimise |  |  |  |  | Minimal 1 | Possible 4 | Low 4
|  | Asbestos or silica |  |  |  | N/A | [7 empty] | N/A
|  | Biological |  |  |  | N/A | [7 empty] | N/A
|  | Confined spaces |  |  |  | N/A | [7 empty] | N/A
|  | Excavation |  |  |  | N/A | [7 empty] | N/A
|  | Extreme Temperature |  |  |  | N/A | [7 empty] | N/A
|  | Fires or Explosions or Hot Work |  |  |  | N/A | [7 empty] | N/A
|  | Hazardous Substances, Chemicals |  |  |  | N/A | [7 empty] | N/A
|  | Health, Wellbeing, Stress, Fatigue |  |  |  | N/A | [7 empty] | N/A
|  | Manual Handling Or Body Stress |  |  |  | N/A | [7 empty] | N/A
|  | Natural Events |  |  |  | N/A | [7 empty] | N/A
|  | Noise |  |  |  | N/A | [7 empty] | N/A
|  | Services – Working With Or Near |  |  |  | N/A | [7 empty] | N/A
|  | Stormwater access risk |  |  |  | N/A | [7 empty] | N/A
|  | Tools And Equipment (Powered Or Hand) |  |  |  | N/A | [7 empty] | N/A
|  | Traffic Or Pedestrian Movement |  |  |  | N/A | [7 empty] | N/A
|  | Vehicles And Mobile Equipment |  |  |  | N/A | [7 empty] | N/A
|  | Water - Being In, Near, Or On |  |  |  | N/A | [7 empty] | N/A
|  | Work Environment (Housekeeping) |  |  |  | N/A | [7 empty] | N/A
|  | Working At Height or Raised and Falling Objects |  |  |  | N/A | [7 empty] | N/A
|  | Working Remotely Or Isolated |  |  |  | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A
[6 empty] | N/A | [7 empty] | N/A

## Guideword checklist
Guideword Checklist
Issues to be considered during the Design |  |  | Communications, e.g. normal, emergency
(Tick ✓ those issues that are applicable – X those that have been discounted) |  |  | Community/public interaction/access
Note: This is not an exhaustive list of potential issues |  |  | Confined space
ü / x | Guideword | Guidance on potential issues to consider
| Access/egress, access ways, entrances/gates | No. of entry/egress points, caught, trapped, emergency egress, obstructions, lighting, external impacts, people and equipment, frequency of movements. How should people enter or exit the site or gain access to individual asset / item? | Construction method
| Adjacent structures | How do structures adjacent to the design affect the design and / or how will the design affect things that surround it? Eg heat, light shadow, geotech stability, fire, access. | Corrosion
| Asbestos | Could asbestos be present, including as material in existing buildings or piping on or adjacent to the site? Is asbestos contained or exposed with the possibility of dust formation? Are risks involving asbestos cement pipes adequately addressed? | Dust/fumes/vapours
| Biological | Does the design use, produce or dispose of substances known to be biological hazards? | Emergency Response
| Carcinogens | Does the design use, produce or dispose of substances known to cause cancer? | Ergonomics
| Chemicals | Does the design use, produce or dispose of chemicals? Where chemicals are required has the design considered the appropriateness of the storage, access and spill requirements for the chemical and/or the alternatives available that may be less harmful to both people and the environment? | Excavation
| Commissioning | How can the act of commissioning generate hazards? | Explosion
| Communications, e.g. normal, emergency | Does the design consider critical communication events such as emergencies (response time) and is there mobile phone coverage? | Electrical
| Community/public interaction/access | Is there public access to the site and does the design provide sufficient controls to prevent harm to the public? | External / 3rd party activities
| Confined space | Are there confined spaces created by the design? Are they indicated on the drawings and are there alternative methods that can be developed/used to eliminate and or reduce the impacts of confined spaces? | Extreme Weather
| Construction interfaces | Does the site interface with other operating works? | Fire
| Construction method | Does the method of construction introduce hazards? What construction options are available? | Fixed plant & equipment
| Corrosion | Does the design consider corrosion due to either the environment or process and take into account materials selection to reduce the impact? | Fatigue
| Demolition | Ease, issues, documentation, asbestos, sequencing. | Flow
| Dust/fumes/vapours | Should these issues be produced and how does the design the minimise them? | Formwork
| Electrical | Underground, overhead, heating, proximity, spacings, clearances, isolation for maintenance access. Is there a risk of electrocution from cutting into metal pipes? Does the design introduce the risk of electric shock in general? | Ground conditions
| Eliminate/combine | Movements, mobile plant, lifting, exertion, sequence, timing, simplify. | Ground water
| Emergency Response | How does the design consider how to provide emergency response? Aspects to consider include provision of first aid, communication, access for emergency services and evacuation. | Hazardous substances/ Dangerous goods
| Ergonomics | Posture, manual handling, RSI, discomfort, fatigue, stress, effect on PPE, visibility, slips, trips. How do humans interact with the design? Are workstations or operator controls designed to allow ease of use for the human body? | High pressure (low pressure)
| Excavation | Should hazards such as excavations collapse be introduced? | Hot Works
| Explosion | Does the design include any substances that could lead to explosion, including gases, liquids or dust? Have sources of ignition been eliminated and monitoring systems been included? | Inspections
| External / 3rd party activities | Security threats e.g. sabotage, terrorist activities | Instability
| Extreme Weather | Has the design included the provision of shelter or reduction of the effect of extreme weather on people? Has the design considered loads capable of withstanding the effects of weather, such as high winds, rain, heat and cold? | Interference between trades
| Falling Objects | Does the design include the possibility of objects being dropped from heights? Has protection been included, including barriers to stop objects from falling and covers to protect from objects that have fallen? | Isolation
| Fatigue | Should the design introduce fatigue issues? | Laydown areas
| Fire | Prevention/detection, suppression/protection, emergency procedures, sparks/earthing. Does the design include flammable or combustible materials? Have fire detection systems and fire fighting systems been implemented? | Lighting
| Fixed plant & equipment | Does the design take into account the location of plant, clear working space and hazards introduced by the plant itself? | Live services
| Flow | Does the design include any process that includes flow? Have hazards associated with too much flow, not enough flow or blockages been considered? | Location
| Formwork | Does the design include formwork during construction? Have hazards such as heights, slips and trips, engulfment and confined spaces been considered? | Maintainability
| Ground conditions | Does the design take into account the general terrain and type of ground? How the asset should alter the ground conditions. | Manual handling
| Ground water | Does groundwater produce the possibility of unstable ground or structural instability? | Materials of construction
| Guarding/fencing/ security | Is plant and equipment guarded appropriately e.g. preventing contact with energies, interlock, tamper proof, fails to safe etc. Does the design provide sufficient security measures to protect the asset | Mobile plant & equipment
| Hazardous substances/ Dangerous goods | Where chemicals are required has the design considered the appropriateness of the storage, access and spill requirements for the chemical and/or the alternatives available that may be less harmful to both people and the environment. | Movement of machinery/contaminants
| Heavy lifts/cranage | Can heavy lifts be removed or minimised? Is there sufficient room to allow access for cranes and for the cranes to operate? | Noise
| Hot Works | Have construction methods and operation taken into account hot work issues. | Piling
| Impact on public roads/traffic | Is there any impacts from traffic on the location of the asset that can eliminate and/or reduce those impacts e.g. service point in road, access of roads, and access for construction, maintenance and operational vehicles. | Pollution/contamination/ spills/releases/emissions
| Inspections | Does the design consider the necessity of inspections and allow for access, lighting, guarding, etc. | Pressure
| Instability | Has instability due to structures or geotechnical conditions been considered? Has industrial process instability been considered? | Public interference
| Interfaces external to the project | Public safety, traffic, adjacent property, services, external fire, day/night/weekend, emergency services, noise, dust, pollution, vibration, departures from standard details or practice. | Radiation
| Interference between trades | Has the interaction between the different trades during construction and operation been considered in the design? | Safety factor
| Isolation | Has the design identified all the energy sources requiring isolation and does the design consider the location and number of isolation points? | Services
| Laydown areas | Does the laydown area provide sufficient space to allow safe access to equipment and are laydown areas located in positions that provide short and unobstructed travel paths? | Slips/Trips/Falls
| Lighting | Has sufficient lighting been provided to allow the design to perform as required and to allow personnel to operate the design as required? | Storage
| Load/force/energy/pressure | High, excess, low, insufficient, additional loads, dynamics, temporary weakness, fragile, tension, compression, PE, inertia, movement, fluid flows. Will there be a risk associated with pipes under pressure? | Stored energy (Mechanical, Electrical)
| Location | Has the design considered the location of the site itself in relation to the environment and other assets surrounding it? Have the locations of the assets within the design been considered with respect to each other and any existing assets already in place? Are different sections of a design compatible to be located beside one another? | Startup/shutdown
| Maintainability | Has the design provided for maintenance of the asset with clear working space provided, lifting device/points provided and the risk hazard such as electricity, heat, pressure and vibration eliminated or reduce as far as is practicable and that appropriate signage (warning, caution, danger) have been specified in the design. | Structures
| Manual handling | Has the design considered mechanical devices for lowering and lifting equipment and is the equipment positioned so it can be retrieved / replaced using mechanical devices and does the equipment have designated designed lifting points. | Temporary works
| Materials of construction | Does the design consider the selection of materials relative to the location of the asset (e.g. can it handle bushfires), construction technique required, maintenance requirements (uniformity v’s mixing) etc. Does the design consider opportunities to source material through reuse or recycled options? | Temperature
| Mobile plant & equipment | Has the movement of mobile plant (includes vehicles) been incorporated in the design? Internal, external, above, below, reversing, visibility. | Vibration
| Movement direction | Stability/instability, compression, physical damage, vibration, friction, slip, rotation, up, downwards, reverse, expansion, tension, rollover. | Visibility
| Movement of machinery/contaminants | Have clear paths for machinery movement been considered in the design to eliminate impacts? This includes impacts with humans, machinery, structures or vehicles. | Water
| Natural hazards | Extreme weather, lightning, dust, temperature, ground, water, snow, ice, noise, earthquake, floods, high wind. | Workplace conditions, extreme temperatures
| Noise | Does the design require noisy processes to be used during construction and is there ways to eliminate and/or reduce these impacts by using construction methodologies. Has plant and equipment that creates noise been appropriately designed to reduce noise e.g. ceramic bearings, dampers, isolated, insulted, balanced to reduce vibration etc | Site caused environment
| Operations, including work practices | Does the design address how the new asset should be operated? | Site layout
| Operations/Interactions | Does the design of the new project interface with existing assets? | Slips/Trips/Falls
| Overhead/Underground Services | Does the design consider the impacts on existing services e.g. striking underground and overhead services, access for construction, maintenance and operational vehicles and plant and excavation and can the design be modified to eliminate and/or reduce the impact associated with the existing services. | Startup/shutdown
| Piling | Have the hazards associated with piling been considered for the piling operation and on the surroundings? Hazards include the stability of piling rig including geotech investigation, dropped weights, heights, excavations, noise and vibration. | Storage
| Pollution/contamination/ spills/releases/emissions | Does the design consider these issues to reduce or eliminate the impacts? | Stored energy (Mechanical, Electrical)
| Position/location | Too high, too low, too far, misaligned, wrong position. | Structures
| Pressure | Does the design include the use of pressure? Have sufficient confinement, materials of construction, testing, pressure relief systems and isolation been considered in the design? Has the design identified plant and equipment that has high pressures stored, the impact of those pressures during maintenance and operation of the asset and the controls to prevent uncontrolled release of those pressures whilst carrying out maintenance and/or emergency operations. | Temperature
| Public interference | Has security of the assets included in the design been incorporated? Has the level of security required based on public perception been considered? | Temporary works
| Radiation | Does the design include radioactive material or the generation of x-rays? Has the design considered containment, screening/shielding, elimination of the requirement, signage, sufficient space requirements around the radiation source and emergency procedures? | Timing
| Safety factor | Does the design have a sufficient engineering over design factor? | Toxicity/safety
| Services | Does the design consider the impacts on existing services e.g. striking underground and overhead services, access for construction, maintenance and operational vehicles and plant and excavation and can the design be modified to eliminate and/or reduce the impact associated with the existing services? | Utilities/services
| Site caused environment | Vapour/dust, effluent/waste, noise, flooding. | Vibration
| Site layout | Surrounding environment, site clearance, access (within and to site), traffic circulation, size, storage space, limitations, contamination, existing infrastructure/structures. | Visibility
| Slips/Trips/Falls | Does the design provide for even surfaces and clear walkways?
| Startup/shutdown | Does the method of startup or shutdown of a process introduce any hazards? Hazards may include isolations, ignition sources, pressure, gravity, speed and temperature.
| Storage | How are storage areas incorporated into the design?
| Stored energy (Mechanical, Electrical) | Does the design address stored energy impacts and provide adequate and appropriate methods to eliminate or reduce those impacts.
| Structures | Does the design incorporate ease of construction and access when constructed?
| Temperature | Does the design include protection from high and low temperatures, including protection for people and the equipment. Is the temperature necessary in the design?
| Temporary works | Does the design / specification detail temporary works requirements e.g. weights of component, temporary lifting points, permanent formwork vs. conventional formwork etc.
| Timing | Too late, early, short, long, sequence, extended delays.
| Toxicity/safety | PPE, chemicals, safety showers, eye wash, barriers/guards, lead/asbestos, oil, handling, precautions, ventilation, gases, pressure venting, overflows (provision), materials.
| Utilities/services | Vapour/dust, effluent/waste, noise, seepage, heat/cold, electricity, flooding, outages, proximity. Have services such as electricity, gas, water, sewer and telecommunications been identified and isolation or relocation of these services been included in the design?
| Vibration | Have the effects of vibration on the human body and the surrounding assets been considered in the design?
| Visibility | Has lack of visibility been considered in the design?
| Water | Does the design consider working in or above water? Have the hazards involved with storm water and ponding been considered?
| Working at heights | Working at heights/depth, falls, striking by falling objects, scaffolding (space to fit). Has the design considered height related impacts and provided adequate and appropriate methods to eliminate and or reduce those impacts?
| Workplace conditions, extreme temperatures | Does the design address the vulnerability to extreme temperatures and provide adequate and appropriate methods to eliminate or reduce those impacts?

## Key risks
Key risk definitions and reference links
Risk Source (Hazard) | Definition | Guidance
Asbestos or Silica | Situations in which people are exposed to asbestos or silica dust. This includes asbestos or silica containing materials, or things that as part of its design, contain asbestos and silica. | Worksafe Mahi Haumaru Aoteroa Asbestos guidance
Assets Or Fixed Plant | Failures in the design, construction and integrity of assets, e.g. buildings, fixed machinery, structures, person access, process infrastructure. Plant such as the equipment at Council facilities, for which either exposure to moving parts or incorrect operation / failure creates the potential for injury. | See the Worksafe Mahi Haumaru Aoteroa website
Biological | Situations in which there is harm to health as a result of exposure to biological hazards, e.g. animals, contaminated water, bacteria, viruses, parasites etc. The harm may be immediate, or may be a long-term consequence of prolonged or repeated exposures. | See the Worksafe Mahi Haumaru Aoteroa website
Confined Spaces | A confined space means an enclosed or partially enclosed space that: ■ is not designed or intended primarily to be occupied by a person; and ■ is, or is designed or intended to be, at normal atmospheric pressure while any person is in the space; and ■ is or is likely to be a risk to health and safety from: o an atmosphere that does not have a safe oxygen level, or o contaminants, including airborne gases, vapours and dusts, that may cause injury from fire or explosion, or o harmful concentrations of any airborne contaminants, or o engulfment. | See HSEP_0003 Confined Space Process
Excavation | Situations in which workers or the public are exposed to injury, if excavations fail | See HSEP_0004 Excavation Safety Process
Extreme Temperature | Situations where extreme temperature could cause damage to property or harm to people. | See the Worksafe Mahi Haumaru Aoteroa guidance on temperature at work
Fires or Explosions or Hot Work | Situations, activities, ignition sources, or atmosphere which result in fire or explosion | See the Worksafe Mahi Haumaru Aoteroa guidance
Hazardous Substances, Chemicals | Chemicals and substances (excluding asbestos or silica) that have the potential to cause injury, illness or damage through inhalation, absorption, ingestion, corrosion, reaction, or through fire or explosion. | See the Worksafe Mahi Haumaru Aoteroa hazardous substances guidance
Health, Wellbeing, Stress, Fatigue | Situations in which there is a risk of harm to the physical and mental health of workers as a consequence of the way in which work is carried out, or factors that affect work. (Includes stress, fatigue, bullying and harassment, personal confrontation, hours of work/ timeframes) | HSEP_0056 Health, Safety and Wellbeing Expectations
Manual Handling Or Body Stress | Any situation in which a task exposes a worker to the risk of a musculoskeletal injury, strain, discomfort, pain or injury, as a consequence of overuse, or a mismatch between the task, or the way the task is performed, and the physical capability of the person for that task. | See the Worksafe Mahi Haumaru Aoteroa manual handling guidance
Natural Events | Situations in which workers are responding to emergencies resulting from extreme weather events and earthquakes, tsunamis, etc. | See the Worksafe Mahi Haumaru Aoteroa natural events and emergencies guidance
Noise | Situations in which there is a risk of hearing loss, discomfort, pain or injury from excessive noise exposure. | See the Worksafe Mahi Haumaru Aoteroa guidance on noise
Services – Working With Or Near | Situations in which workers or the public are exposed to injury, if Council work contacts or damages services, in particular gas and electricity. | See the Worksafe Mahi Haumaru Aoteroa guidance on working near utilities and services
Stormwater access risk | Is, or is likely, to be a risk to health and safety for access around certain stormwater infrastructure, including inlets, outlets, wetlands and retention dams.
Tools And Equipment (Powered Or Hand) | The use of tools and equipment that lead to actual or potential injury. Or the lack/mismatch of appropriate equipment for the task. | HSEP_0056 Health, Safety and Wellbeing Expectations
Traffic Or Pedestrian Movement | This covers potential sources of harm to members of the public and workers when work activities are being undertaken. This may include on WWL premises where public or worker exclusion is required. | See the Worksafe Mahi Haumaru Aoteroa guidance on working near live traffic
Vehicles And Mobile Equipment | Two or four-wheeled vehicles that are permitted for use on public roads or off-road. Other types of mobile equipment/machinery, (fork-lifts, specialist road working equipment, brush chippers, diggers, rollers, tractors, mobile elevated work platforms). Includes attachments such as trailers, winches etc. | See the Worksafe Mahi Haumaru Aoteroa guidance on vehicles and mobile plant
Water - Being In, Near, Or On | Work or public presence in any situation in which a person could lose consciousness or drown as a result of immersion in water. | HSEP_0056 Health, Safety and Wellbeing Expectations
Work Environment (Housekeeping) | Situations in which there is a risk of injury as a consequence of layout, space, lighting, ventilation, temperature, noise, uneven/slippery surfaces, or obstacles in the environment, indoors or outdoors. e.g. materials stored in either racks (archived documents, tools and equipment), as well as stockpiles and storage of natural materials and waste. | HSEP_0056 Health, Safety and Wellbeing Expectations
Working At Height or Raised and Falling Objects | ■ Work carried out in any situation in which a worker could fall from height. ■ Work carried out in any situation where people could be injured by falling objects from an overhead activity. | HSEP_0025 Working at Heights Process
Working Remotely Or Isolated | People working to the exclusion of others (regardless of location) and by nature of the work or environment could be exposed to a risk of serious harm. It includes after hours work in an office or where sites need appropriate consideration of hazards because of its geographical location. | See the Worksafe Mahi Haumaru Aoteroa guidance

## Consequence
Group | Consequence Score | Analysis Cost | Harm to People | Harm to the Environment | Service delivery | Financial Impact | Reputation and Organisational Integrity
Substantial | 100 | 5800000 | Multiple deaths/permanent disabilities. | Environmental damage which takes more than 1 year to restore or is permanent | Service disruption greater than 6 hours affecting 10 - <100 residential or 2 - <10 commercial customers | >$5,000,000 | Sustained national media coverage (months) or international media coverage
Major | 70 | 4000000 | Death/permanent disability or multiple long-term disabilities. Area-wide serious illness, mediacl treatment reqiored by more than 20 people, or 1 fatality. | Environmental damage repaired within 6 – 12 months | Minor 3rd party business continuity issues | $3,300,000 - $5,000,000 | Unfavourable national publicity Major PR control required
Moderate | 40 | 2300000 | Medical attention/ hospitalisation required for up to 20 people. Isolated cases of serious illness, or system-wide cases of significant illness. Irreversable health effect. Loss time injury > 1 week. | Environmental damage repaired within 1 – 5 months | Service disruption greater than 6 hours affecting <10 residential or a commercial customer | $1,200,000 - $3,300,000 | Unfavourable regional publicity Significant PR control required
Minor | 10 | 600000 | Medical attention required for up to 5 people. Hospitalisation required for some. Isolated cases of significant illness or system-wide cases of minor illness. Loss time injury < 1week. | Environmental damage repaired within 4 weeks | Reduction in levels of service >6 hours | $120,000 - $1,200,000 | Local media coverage for 1-5 days. Some PR controls required
Minimal | 1 | 60000 | Injury requiring short term treatment/First Aid Isolated reports of minor illness. No discernable health effect. | Environmental damage repaired within 7 days | Short term (<6 hours) reduction in levels of service | <$120,000 | Local media coverage for 1 day
Not Applicable | 0 | 0 | No injuries No impact on public health | No environmental impact | No impact on service delivery | No additional cost | No media coverage or adverse impact on reputation

## Likelihood
Group | Rare | Highly Unlikely | Unlikely | Possible | Likely
Likelihood Score | 1 | 2 | 3 | 4 | 5
Frequency | Is expected to occur within a 100 year timeframe | Is expected to occur within a 50 year timeframe | Is expected to occur within a 10 year timeframe | Is expected to occur within a 2 year timeframe | Is expected to occur within a 1 year timeframe
Annual probability | 1% chance of occurring in any year | 2% chance of occurring in any year | 10% chance of occurring in any year | 50% likelihood of occurring in any year | 90% likelihood of occurring in any year
Note: The likelihood score is independent from the project length. If you’re working on a short project (e.g. less than six months), and assign the likelihood regardless of the project length.

## Risk table
Likelihood
| Category | Rare 1 | Highly Unlikely 2 | Unlikely 3 | Possible 4 | Likely 5
Consequence | Substantial 100 | Moderate (100) | High (200) | High (300) | Extreme (400) | Extreme (500)
| Major 70 | Moderate (70) | Moderate (140) | High (210) | High (280) | Extreme (350)
| Moderate 40 | Low (40) | Moderate (80) | Moderate (120) | Moderate (160) | High (200)
| Minor 10 | Low (10) | Low (20) | Low (30) | Low (40) | Low (50)
| Minimal 1 | Low (1) | Low (2) | Low (3) | Low (4) | Low (5)

## Lists
| Rare 1 | Highly Unlikely 2 | Unlikely 3 | Possible 4 | Likely 5
Substantial 100 | Moderate 100 | High 200 | High 300 | Extreme 400 | Extreme 500 | Stormwater - Chamber | 500 Extreme | Extreme 500 | 500 Extreme
Major 70 | Moderate 70 | Moderate 140 | High 210 | High 280 | Extreme 350 | Stormwater – Channel | 400 Extreme | Extreme 400 | 400 Extreme
Moderate 40 | Low 40 | Moderate 80 | Moderate 120 | Moderate 160 | High 200 | Stormwater – Culvert | 350 Extreme | Extreme 350 | 350 Extreme
Minor 10 | Low 10 | Low 20 | Low 30 | Low 40 | Low 50 | Stormwater - Field Drain | 300 High | High 300 | 300 High
Minimal 1 | Low 1 | Low 2 | Low 3 | Low 4 | Low 5 | Stormwater – Flume | 280 High | High 280 | 280 High
[6 empty] | Stormwater - Inlet | 210 High | High 210 | 210 High
[6 empty] | Stormwater - Inlet Gridded | 200 High | High 200 | 200 High
| Rare 1 | Highly Unlikely 2 | Unlikely 3 | Possible 4 | Likely 5 | Stormwater - Lamphole | 160 Moderate | Moderate 160 | 160 Moderate
Substantial 100 | 100 | 200 | 300 | 400 | 500 | Stormwater - Lateral | 140 Moderate | Moderate 140 | 140 Moderate
Major 70 | 70 | 140 | 210 | 280 | 350 | Stormwater - Manhole | 120 Moderate | Moderate 120 | 120 Moderate
Moderate 40 | 40 | 80 | 120 | 160 | 200 | Stormwater - Outlet | 100 Moderate | Moderate 100 | 100 Moderate
Minor 10 | 10 | 20 | 30 | 40 | 50 | Stormwater - Overflow | 80 Moderate | Moderate 80 | 80 Moderate
Minimal 1 | 1 | 2 | 3 | 4 | 5 | Stormwater – Overflow | 70 Moderate | Moderate 70 | 70 Moderate
[6 empty] | Stormwater - Pipe | 50 Low | Low 50 | 50 Low
Initial H&S Risk Assessment (Step II) | [5 empty] | Stormwater - Pressure Main | 40 Low | Low 40 | 40 Low
Review H&S Risk Assessment (Step IV) |  |  |  | Yes |  | Stormwater - Pump | 30 Low | Low 30 | 30 Low
Peer Review H&S Risk Assessment (Step VI) |  |  |  | No |  | Stormwater - Pumping Station | 20 Low | Low 20 | 20 Low
Design H&S Risk Assessment (Step VII) |  |  |  | Not Applicable |  | Stormwater - Rising Main | 10 Low | Low 10 | 10 Low
Specialist H&S Risk Assessment (Step IX) | [5 empty] | Stormwater - Sump | 5 Low | Low 5 | 5 Low
Pre-Construction H&S Risk Assessment (Step XI) | [5 empty] | Stormwater – Sump Lead | 4 Low | Low 4 | 4 Low
Reconsidered H&S Risk Assessment during Construction (Step XV) | [5 empty] | Stormwater – Syphon | 3 Low | Low 3 | 3 Low
Post-Construction H&S Risk Assessment (Step XVI) | [5 empty] | Stormwater – Tunnel | 2 Low | Low 2 | 2 Low
[6 empty] | Stormwater - Wet Well | 1 Low | Low 1 | 1 Low
[6 empty] | Strormwater - Valve | N/A | N/A | N/A
Minimal 1 | Rare 1 |  | Asset Manager |  |  | Wastewater - Interceptor
Minor 10 | Highly Unlikely 2 |  | Investigator |  |  | Wastewater - Lateral
Moderate 40 | Unlikely 3 |  | Designer |  |  | Wastewater - Overflow
Major 70 | Possible 4 |  | Project Manager |  |  | Wastewater - Pipe
Substantial 100 | Likely 5 |  | Operator |  |  | Wastewater - Rising Main
N/A |  |  | Maintainer |  |  | Wastewater - Syphon
|  |  | Contractor |  |  | Wastewater - Chamber
Eliminate |  |  | Contracts Officer |  |  | Wastewater - Dry Well
Minimise |  |  | Property Owner |  |  | Wastewater - Lamphole
|  |  | Property Representative |  |  | Wastewater - Manhole
|  |  | Specialist |  |  | Wastewater - Pump
1. Substitute | [5 empty] | Wastewater - Pumping Station
1. Isolate | [5 empty] | Wastewater - Valve
1. Engineering Control | [5 empty] | Wastewater - Wet Well
2. Adminstration Control | [5 empty] | Wastewater -Treatment Plant
3. PPE | [5 empty] | Water - Inlet
Water - Bulk Main
Water - Hydrant
Water - Meter
Water - Outlet
Hazardous substances |  |  |  | Phase 1 Define |  | Water - Pipe
Hazardous energy |  |  |  | Phase 2 Plan |  | Water - Pump
Excavations, trenching, tunnelling |  |  |  | Phase 3 Concept design |  | Water - Pump Station
Confined spaces |  |  |  | Phase 4 Detailed design |  | Water - Reservoir
Working at heights |  |  |  | Phase 5 Procure |  | Water - Rider Main
Lifting operations |  |  |  | Phase 6 Construct |  | Water - Rising Main
Aggression and violence |  |  |  | Phase 7 Complete |  | Water - Scour Pipe
Water - Service Pipe
Traffic management | [5 empty] | Water - Treatment Plant
Driving | [5 empty] | Water - Valve
Fatigue
Mobile plant and equipment
Fixed plant and equipment